## Planned_vs_Actual_Sprint
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Setup, Layered Architecture & DB Configuration | MUST HAVE | No Dependency | Harika | Completed
S1 | S1 | US-002 | Transaction Data Modeling | MUST HAVE | US-001 | Harika | Completed
S2 | S2 | US-003 | Fraud Dataset & Rule Definition | MUST HAVE | US-002 | Harika | Completed
S2 | S2 | US-004 | Transaction Simulation Engine | MUST HAVE | US-003 | Harika | Completed
S3 | S3 | US-005 | Rule-Based Detection Engine | MUST HAVE | US-004 | Harika | Completed
S3 | S3 | US-006 | Dashboard & Monitoring Hub | MUST HAVE | US-005 | Harika | Completed
S4 | S4 | US-007 | REST API Gateway Integration | MUST HAVE | US-006 | Harika | Completed
S4 | S4 | US-008 | ML Plug-in Integration & Deployment | MUST HAVE | US-007 | Harika | Completed

## Sprint_1_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity Status | Original Estimate Effort (In Hours) | Day 1 Pending Hours | Day 2 Pending Hours | Day 3 Pending Hours | Day 4 Pending Hours | Day 5 Pending Hours | Day 6 Pending Hours | Day 7 Pending Hours | Day 8 Pending Hours | Day 9 Pending Hours | Day 10 Pending Hours | Day 11 Pending Hours | Day 12 Pending Hours | Day 13 Pending Hours | Day 14 Pending Hours
US-001 | 1 | Environment Setup | 30-Dec-2025 | 02-Jan-2026 | Harika | 3-Completed | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Transaction Data Modeling | 31-Dec-2025 | 03-Jan-2026 | Harika | 3-Completed | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint_2_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity Status | Original Estimate Effort (In Hours) | Day 1 Pending Hours | Day 2 Pending Hours | Day 3 Pending Hours | Day 4 Pending Hours | Day 5 Pending Hours | Day 6 Pending Hours | Day 7 Pending Hours | Day 8 Pending Hours | Day 9 Pending Hours | Day 10 Pending Hours | Day 11 Pending Hours | Day 12 Pending Hours | Day 13 Pending Hours | Day 14 Pending Hours
US-003 | 1 | Fraud Dataset Preparation | 13-Jan-2026 | 16-Jan-2026 | Harika | 3-Completed | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 2 | Transaction Simulation Engine | 14-Jan-2026 | 17-Jan-2026 | Harika | 3-Completed | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint_3_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity Status | Original Estimate Effort (In Hours) | Day 1 Pending Hours | Day 2 Pending Hours | Day 3 Pending Hours | Day 4 Pending Hours | Day 5 Pending Hours | Day 6 Pending Hours | Day 7 Pending Hours | Day 8 Pending Hours | Day 9 Pending Hours | Day 10 Pending Hours | Day 11 Pending Hours | Day 12 Pending Hours | Day 13 Pending Hours | Day 14 Pending Hours
US-005 | 1 | Rule-Based Detection Engine | 27-Jan-2026 | 30-Jan-2026 | Harika | 3-Completed | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 2 | Dashboard Development | 28-Jan-2026 | 31-Jan-2026 | Harika | 3-Completed | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint_4_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity Status | Original Estimate Effort (In Hours) | Day 1 Pending Hours | Day 2 Pending Hours | Day 3 Pending Hours | Day 4 Pending Hours | Day 5 Pending Hours | Day 6 Pending Hours | Day 7 Pending Hours | Day 8 Pending Hours | Day 9 Pending Hours | Day 10 Pending Hours | Day 11 Pending Hours | Day 12 Pending Hours | Day 13 Pending Hours | Day 14 Pending Hours
US-007 | 1 | API Gateway Integration | 10-Feb-2026 | 13-Feb-2026 | Harika | 3-Completed | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 2 | ML Integration & Deployment | 11-Feb-2026 | 14-Feb-2026 | Harika | 3-Completed | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Impediments_Log
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Fraud logic confusion | Discussed with mentor
Sprint 2 | Day 7 | High false positives | Adjusted rule thresholds
Sprint 3 | Day 6 | API validation errors | Improved payload validation
Sprint 4 | Day 10 | ML overfitting | Applied cross-validation

## Retrospective
SL # | Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 29-Dec-2025 | 11-Jan-2026 | Harika | Requirement clarity | Assumptions | Mentor discussions | Clear project base formed
2 | Sprint 2 | 12-Jan-2026 | 25-Jan-2026 | Harika | Modular coding | Hardcoding | Testing rules | Reduced false positives
3 | Sprint 3 | 26-Jan-2026 | 08-Feb-2026 | Harika | API documentation | Ignoring warnings | Integration testing | Stable dashboard achieved
4 | Sprint 4 | 09-Feb-2026 | 23-Feb-2026 | Harika | Model tuning | Overfitting | Performance benchmarking | Improved ML accuracy